CONTRACT MODIFICATION REQUEST FAR 43.103 — Bilateral or Unilateral Mod · Standard Form 30 (SF-30)

| TO | Contracting Officer name, title, agency | FROM | Company name, POC name, phone |
| --- | --- | --- | --- |
| DATE | MM/DD/YYYY | CONTRACT # | [PIID / contract number] |
| MOD TYPE | ☐ Bilateral (FAR 43.103(a)) ☐ Unilateral (FAR 43.103(b)) ☐ Administrative Change |  |  |

| 1. MODIFICATION REQUEST SUMMARY In one sentence, describe what you are asking the Contracting Officer to change — e.g., "Request a no-cost 30-day extension to the Period of Performance under CLIN 0001, from [current end date] to [new end date], due to government-caused delay in facility access." [Replace the entire sentence with your own.] 2. REASON FOR MODIFICATION Select one reason and delete the others: ☐ Government Convenience (FAR 52.249-2) — the agency directed the change; contractor is not at fault ☐ Contractor Request — company is requesting relief, funding change, or scope update ☐ Scope Clarification — existing PWS/SOW language is ambiguous and requires interpretive correction ☐ No-Cost Extension — additional time is needed to complete deliverables at no additional cost to the government ☐ Request for Equitable Adjustment (REA) — contractor incurred additional costs due to a government action or change order [After selecting the reason above, write one paragraph explaining the specific circumstances — what happened, when it happened, and how it connects to the reason selected. Reference contract sections, CDRLs, CLINs, or dates as applicable.] 3. SPECIFIC CHANGE REQUESTED Clause / Section; [FAR clause, PWS §, or CLIN reference — e.g., FAR 52.212-4(l)]. Line Item (CLIN); [CLIN 0001, 0002-AA, etc. — or "N/A"]. Quantity / Amount; [Revised qty or dollar amount — or "No change"]. Period of Performance; [Current end date → proposed new end date — or "No change"]. Deliverable / CDRL; [DD-XXXX-XXXX or deliverable title — or "N/A"]. 4. COST IMPACT Cost Impact; ☐ No Cost ☐ Additional Cost: $_____________ ☐ Cost Reduction: $_____________. Schedule Impact; ☐ No Change ☐ Extension of ______ calendar days ☐ Acceleration. 5. JUSTIFICATION Provide three paragraphs. Keep each to 4–6 sentences. Paragraph 1 — Background and contract history: [Describe the original scope, award date, period of performance, and any prior modifications. Cite the contract number and any relevant option periods. Keep it factual — CO doesn't need the sales pitch, just the history.] Paragraph 2 — What changed and why: [Explain the triggering event — a government-directed change under FAR 43.202, an unforeseen condition, a funding realignment, or a scope clarification. Be specific: name the date, the government representative who directed the change, and the corresponding email or meeting record (reference as Attachment A if applicable).] Paragraph 3 — Why this mod is in the government's best interest: [Explain how approving this modification protects mission continuity, avoids re-procurement costs, or preserves a key deliverable. Include any cost-avoidance math if relevant. Close with a sentence offering to provide a cost and pricing proposal, an independent government estimate reconciliation, or a schedule recovery plan at the CO's request.] 6. POINT OF CONTACT & SIGNATURE By signing below, the contractor certifies that the information in this request is accurate and complete, and that no work has begun on any proposed additional scope prior to CO authorization. Authorized Signature: ________________________________________________ Printed Name: ________________________________________________ Title: ________________________________________________; Date: ________________________________________________ Phone: ________________________________________________ Email: ________________________________________________. Attachments referenced: ☐ Email/memo directing the change ☐ REQ cost proposal ☐ Updated schedule ☐ Other: ___________ | 5 MOD TYPES WORTH KNOWING 1. Administrative Change Fixes clerical errors — wrong POC, address, DUNS/UEI update. Unilateral (FAR 43.101). No cost or scope change. CO issues it; no contractor signature needed. 2. No-Cost Extension Extends Period of Performance without adding money. Must show government caused the delay or that the work is still achievable. Bilateral — both parties sign. 3. Change Order / Equitable Adjustment Government directs a change under FAR 43.202; contractor submits a Request for Equitable Adjustment (REA) for additional cost + time. Track every hour from day the change is directed. 4. Supplemental Agreement Negotiated, mutually agreed modification — new CLIN, added scope, revised specs. Fully bilateral. Most common vehicle for exercising options out-of-sequence. 5. Termination Settlement Mod Settles costs after a partial or total termination (T4C or T4D). Use FAR 49.206 procedures. File the settlement proposal within 1 year of notice or risk losing cost recovery. PRO TIP The CO can't start negotiating your REA until it's in writing. Even an informal email from the COR counts as a mod trigger under FAR 43.103(b)(3) — document it, date-stamp it, and attach it here as Exhibit A.. Key FAR refs: 43.101, 43.102, 43.103, 43.201, 43.202, 43.301 |
| --- | --- |

capturepilot.com  ·  Federal Lead Kit · Contract Modification Request Template  ·  FAR Part 43