## Instructions
PROPOSAL COMPLIANCE MATRIX — HOW TO USE
Tracks every Section L instruction and Section M evaluation factor so nothing slips between RFP release and submission. Built for owners with a proposal due in 30 days and zero government bid experience.
1. Setup
Open Section L Matrix tab. Fill in the solicitation number, RFP release date, due date, proposal manager, and last-updated date at the top. The Completion Summary auto-counts the rest.
2. Section L
Read Section L of the RFP line by line. Add one row per instruction (e.g. L.4.1, L.4.1.1, L.5.2). Paste the exact text — don't paraphrase. Assign a writer. Pick a status from the dropdown. Anything left as 'Not Started' 72 hours before Gold Team is a blocker.
3. Section M
Open Section M Alignment tab. List every evaluation factor and sub-factor. Write a real discriminator in column D — 'We have experience' isn't one. 'We reduced system downtime by 34% on Contract X' is. Pink Team scores it 1-5, Red Team scores it 1-5, the gap column flags weak factors.
4. Submission Checklist
Open Submission Checklist tab 24-48 hours before the deadline. Walk every line top to bottom with the proposal manager. Anything Failing or N/A needs a note. The sign-off row at the bottom is the go/no-go.
5. Help
Open Help tab for a worked example based on a real Army janitorial RFP. Shows what good rows look like and what 'Reviewed' really means.
STATUS LEGEND
Not Started | Section has no writer or no draft. Check every day during the Proposal Development Period.
In Draft | Writer has started but not finished. Flag if stuck more than 24 hours.
Complete | Writer says they are done. Section is ready for color team review.
Reviewed | Color team has read it and the writer has incorporated comments. This is the only status that counts at Gold Team.
Missing | Section L instruction exists in the RFP but no proposal section addresses it. Compliance gap. Fix it today.
Critical rule: every row in the Section L Matrix must reach 'Reviewed' before Gold Team review. Any 'Not Started' or 'Missing' at Gold Team is a go/no-go blocker. The proposal manager owns this — not the writers, not the reviewers.
Operator note (Andre): boarding at 04:00 with incomplete intel, we learned to track every requirement on a single sheet because once you're on deck nobody has time to flip through binders. Same logic here. One sheet. Every L. Every M. If it isn't on the matrix it doesn't exist.

## Section L Matrix
SECTION L COMPLIANCE MATRIX
One row per Section L instruction. Every row must reach 'Reviewed' before Gold Team. Paste exact RFP text — paraphrasing misses sub-requirements.
Solicitation #: |  |  |  |  | COMPLETION SUMMARY |  | Count | % | Status
RFP Release Date: |  |  |  |  | Total instructions logged
Proposal Due Date: |  |  |  |  | Reviewed
Proposal Manager: |  |  |  |  | Complete (not reviewed)
Last Updated: |  |  |  |  | In Draft + Not Started
Missing (compliance gap)
Critical priority still open
Google Sheets: cells render as native checkboxes. Excel 365: cells render as boolean dropdowns; right-click > Format Cell > Checkbox to convert. Older Excel: cells show as TRUE/FALSE dropdowns.
RFP Reference (L.X.X) | Instruction / Requirement (paste exact RFP text) | Volume | Proposal Section | Page # | Page Limit Impact? | Writer / Owner | Status | Priority | Notes / Open Questions | Status (asset-spec) | Compliant?
VOLUME I — TECHNICAL | [9 empty] | Not Started | FALSE
L.4.1 | The offeror shall describe its technical approach to accomplishing all tasks in the Performance Work Statement (PWS). The description shall address each PWS task area. | Technical | Section 2.0 — Technical Approach |  | Y |  | Not Started | Critical |  | Not Started | FALSE
L.4.1.1 | Describe the methodology and tools used for the primary service area. Include data flow diagrams where applicable. | Technical | Section 2.1 — Methodology |  | Y |  | Not Started | Critical |  | Not Started | FALSE
L.4.1.2 | Identify risks to performance and describe specific mitigation strategies. | Technical | Section 2.4 — Risk Management |  | Y |  | Not Started | High |  | Not Started | FALSE
L.4.1.3 | Describe any innovative approaches, automation, or technology differentiators. | Technical | Section 2.5 — Innovation |  | Y |  | Not Started | High |  | Not Started | FALSE
L.4.2 | Provide a transition plan for assuming responsibility from the incumbent, including a detailed schedule with milestones for the first 90 days. | Technical | Section 2.6 — Transition Plan |  | Y |  | Not Started | Critical |  | Not Started | FALSE
L.4.3 | Provide a Quality Control Plan addressing how the offeror will monitor and measure performance against the PWS metrics. | Technical | Section 2.7 — Quality Control |  | Y |  | Not Started | High |  | Not Started | FALSE
VOLUME II — MANAGEMENT | [9 empty] | Not Started | FALSE
L.5.1 | Provide an organizational chart showing all proposed key and non-key personnel, their roles, and reporting structure. | Management | Section 3.1 — Organization |  | Y |  | Not Started | High |  | Not Started | FALSE
L.5.2 | Provide resumes for all Key Personnel named in Section J. Resumes must be limited to 2 pages per individual. | Management | Attachment A — Resumes |  | N |  | Not Started | Critical |  | Not Started | FALSE
L.5.3 | Describe the management approach, including how the Program Manager will interface with the Contracting Officer's Representative (COR). | Management | Section 3.2 — Management Approach |  | Y |  | Not Started | High |  | Not Started | FALSE
L.5.4 | If any work will be subcontracted, identify proposed subcontractors and their roles, qualifications, and percentage of work. | Management | Section 3.4 — Subcontracting |  | Y |  | Not Started | High |  | Not Started | FALSE
L.5.5 | Provide a staffing plan addressing how key vacancies will be filled and how retention will be maintained. | Management | Section 3.3 — Staffing Plan |  | Y |  | Not Started | High |  | Not Started | FALSE
VOLUME III — PAST PERFORMANCE | [9 empty] | Not Started | FALSE
L.6.1 | Provide no more than X relevant past performance references for work of a similar nature, scope, and complexity completed within the past 5 years. Each reference shall be no longer than X pages. | Past Performance | Section 4.0 — Past Performance |  | Y |  | Not Started | Critical |  | Not Started | FALSE
L.6.1.1 | For each reference, provide: contract number, award amount, period of performance, customer name, and a current POC with phone number and email. | Past Performance | Section 4.0 — PP References |  | Y |  | Not Started | Critical |  | Not Started | FALSE
L.6.1.2 | Describe the scope of work performed, similarities to the current requirement, and key outcomes achieved. | Past Performance | Section 4.0 — PP Narratives |  | Y |  | Not Started | High |  | Not Started | FALSE
L.6.2 | If offeror does not have directly relevant federal past performance, describe relevant commercial or subcontract experience. | Past Performance | Section 4.1 — Commercial Analogues |  | Y |  | Not Started | Medium |  | Not Started | FALSE
VOLUME IV — PRICE / COST | [9 empty] | Not Started | FALSE
L.7.1 | Complete the pricing schedule (Schedule B / CLIN structure) in the format provided as Attachment X to Section J. | Price | Attachment B — Pricing Schedule |  | N |  | Not Started | Critical |  | Not Started | FALSE
L.7.2 | Provide a Basis of Estimate (BOE) for each CLIN, identifying the labor categories, hours, and rates proposed. | Price | Price Narrative — BOE |  | Y |  | Not Started | Critical |  | Not Started | FALSE
L.7.3 | Provide a complete listing of proposed labor categories, associated labor rates by year, and narrative justification for each rate. | Price | Price Narrative — Labor Rates |  | Y |  | Not Started | High |  | Not Started | FALSE
L.7.4 | Certify that all cost or pricing data submitted are accurate, complete, and current as of the date of agreement on price (if CAS/TINA applies). | Price | Price Certification |  | N |  | Not Started | Medium |  | Not Started | FALSE
SECTION J — ATTACHMENTS / ADMIN | [9 empty] | Not Started | FALSE
L.3.1 | Complete, sign, and return Representations and Certifications (FAR 52.204-8) as part of the proposal. | Admin | Attachment — Reps & Certs |  | N |  | Not Started | Critical |  | Not Started | FALSE
L.3.2 | Complete and sign SF-33 (if applicable) or provide the required cover page per Section L instructions. | Admin | Cover Page / SF-33 |  | N |  | Not Started | Critical |  | Not Started | FALSE
L.3.3 | Provide proof of active SAM.gov registration. | Admin | Admin Volume / Cover |  | N |  | Not Started | High |  | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE

## Section M Alignment
SECTION M ALIGNMENT — EVALUATION FACTORS & DISCRIMINATORS
Map each Section M evaluation factor to your proposal sections. Column D is the discriminator that makes you the best-value choice. 'We have experience' is not a discriminator.
SCORING SUMMARY (auto-calculates) |  |  |  |  | Pink Avg | Red Avg | Avg Gap | Status
Average across all rated factors (rows 6 to 100). Blanks ignored.
Eval Factor / Sub-Factor (Section M reference) | Relative Importance | Proposal Section(s) Addressing This Factor | Key Win Theme / Discriminator | Proof Points (past perf / metrics) | Pink Team Score (1-5) | Red Team Score (1-5) | Gap (Red - Pink) | Gap / Open Issue | Owner | Status | Compliant?
FACTOR 1: TECHNICAL APPROACH | [9 empty] | Not Started | FALSE
1.1 Understanding of Requirements | Most Important | [8 empty] | Not Started | FALSE
1.2 Technical Methodology | Most Important | [8 empty] | Not Started | FALSE
1.3 Innovation / Unique Technical Approach | Important | [8 empty] | Not Started | FALSE
1.4 Risk Management | Important | [8 empty] | Not Started | FALSE
FACTOR 2: MANAGEMENT APPROACH | [9 empty] | Not Started | FALSE
2.1 Program Management Plan | Important | [8 empty] | Not Started | FALSE
2.2 Key Personnel Qualifications | Important | [8 empty] | Not Started | FALSE
2.3 Staffing Plan and Retention | Important | [8 empty] | Not Started | FALSE
2.4 Subcontracting / Teaming Strategy | Less Important | [8 empty] | Not Started | FALSE
FACTOR 3: PAST PERFORMANCE | [9 empty] | Not Started | FALSE
3.1 Relevance of Past Performance | Important | [8 empty] | Not Started | FALSE
3.2 Quality of Past Performance (CPARS) | Important | [8 empty] | Not Started | FALSE
3.3 Past Performance of Key Subs | Less Important | [8 empty] | Not Started | FALSE
FACTOR 4: PRICE / COST (separately evaluated) | [9 empty] | Not Started | FALSE
4.1 Total Evaluated Price | N/A — Evaluated separately | [8 empty] | Not Started | FALSE
4.2 Price Realism / Reasonableness | N/A — Evaluated separately | [8 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
[10 empty] | Not Started | FALSE
Key rule: every evaluation factor needs an explicit discriminator in Column D. 'We have experience' is not a discriminator. 'We reduced system downtime by 34% on Contract HQ0034-22-C-0017' is. If you can't write one, you don't have one yet — and that's a capture gap, not a writing gap.

## Submission Checklist
FINAL SUBMISSION CHECKLIST — RUN 24-48 HOURS BEFORE DEADLINE
Every item must read PASS before submission. Anything else needs a note explaining why. The proposal manager owns the sign-off row at the bottom.
CHECKLIST PROGRESS (auto) |  | Pass | Fail | N/A | Go/No-Go
Counts run across rows 6 to 60.
Category | Check Item | Pass / Fail / N/A | Verified By | Time Verified | Notes | Compliant?
PAGE LIMITS | [5 empty] | FALSE
Page Limits | Page count verified against Section L limits — EVERY volume separately |  |  |  |  | FALSE
Page Limits | Cover pages, TOC, resumes, and required forms excluded per RFP instructions |  |  |  |  | FALSE
FORMAT | [5 empty] | FALSE
Format | Font type and size match Section L requirements throughout every volume |  |  |  |  | FALSE
Format | Margins are correct (typically 1 inch) — verified on every page including headers/footers |  |  |  |  | FALSE
Format | Headers/footers include required fields: solicitation #, offeror name, volume name, page # |  |  |  |  | FALSE
Format | All pages are numbered within each volume (re-starts at 1 for each volume if required) |  |  |  |  | FALSE
SECTION L COMPLIANCE | [5 empty] | FALSE
Section L | Section L compliance matrix shows 'Reviewed' status for every instruction row |  |  |  |  | FALSE
Section L | Every 'Complete' item has been reviewed by at least one reviewer other than the writer |  |  |  |  | FALSE
SECTION M ALIGNMENT | [5 empty] | FALSE
Section M | Every evaluation factor has an explicit discriminator stated in the proposal |  |  |  |  | FALSE
ATTACHMENTS | [5 empty] | FALSE
Attachments | All Section J attachments are present, signed, and dated (SF-33, SF-1449, Reps & Certs) |  |  |  |  | FALSE
Attachments | Key personnel letters of commitment are signed and included |  |  |  |  | FALSE
Attachments | Teaming/subcontractor agreements are included (if required by RFP) |  |  |  |  | FALSE
Attachments | Past performance POC names and phone numbers are verified as current (call them) |  |  |  |  | FALSE
PRICING | [5 empty] | FALSE
Pricing | Price/cost schedule math verified — all CLINs sum to correct totals |  |  |  |  | FALSE
Pricing | Pricing format matches Schedule B / CLIN structure exactly (no added or missing CLINs) |  |  |  |  | FALSE
Pricing | Unit prices, quantities, and evaluated prices are consistent with technical assumptions |  |  |  |  | FALSE
Pricing | Multi-year escalation applied correctly (verify against Wage Determination years if SCA) |  |  |  |  | FALSE
SUBMISSION | [5 empty] | FALSE
Submission | Submission method confirmed in writing (SAM.gov portal / email / hand delivery / mail) |  |  |  |  | FALSE
Submission | File names comply with RFP naming conventions (exact format) |  |  |  |  | FALSE
Submission | File sizes are within any portal upload limits — tested with a dummy upload if uncertain |  |  |  |  | FALSE
Submission | Submission deadline verified including TIME ZONE (Eastern Time applies to most federal solicitations) |  |  |  |  | FALSE
Submission | Late submission contingency plan documented (alternate submitter identified) |  |  |  |  | FALSE
Submission | Confirmation of receipt mechanism understood — screenshot / email / portal confirmation expected |  |  |  |  | FALSE
PROOFING | [5 empty] | FALSE
Proofing | Spell check and grammar check completed — proposal manager sign-off confirmed |  |  |  |  | FALSE
Proofing | No placeholder text remains ([INSERT], TBD, XXXX, [Client Name]) in any volume |  |  |  |  | FALSE
Proofing | No prior client or competitor names from boilerplate (search for common names) |  |  |  |  | FALSE
Proofing | All cross-references (see Section X, Figure Y, Attachment Z) are verified as accurate |  |  |  |  | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
Google Sheets: cells render as native checkboxes. Excel 365: cells render as boolean dropdowns; right-click > Format Cell > Checkbox to convert. Older Excel: cells show as TRUE/FALSE dropdowns.
SIGN-OFF: Proposal Manager ______________________________ Date / Time ______________________________ All Critical items confirmed PASS.

## Help
WORKED EXAMPLE — ARMY JANITORIAL RFP
Real-world example based on a Fort Bragg janitorial sources sought (NAICS 561720). Shows what a good Section L row and a good Section M discriminator look like — and what 'Reviewed' actually means in practice.
Section L row — good vs bad
• | Bad: RFP Ref = 'L.4', Instruction = 'technical stuff', Section = 'Tech', Status = 'In Draft', Notes = blank.
• | Good: RFP Ref = 'L.4.1.2', Instruction = 'Identify risks to performance and describe specific mitigation strategies' (exact quote), Volume = Technical, Section = '2.4 Risk Management', Page = 14, Writer = 'M. Hernandez', Status = 'Reviewed', Priority = High, Notes = 'Linked to L.4.2 transition plan; mitigation matrix on p.15'.
• | What makes the good one work: exact RFP citation, exact RFP language, real human owner, cross-reference to related sections, real page number once draft exists.
Section M discriminator — good vs bad
• | Bad: 'We have experience with federal janitorial.' (Every offeror writes this. Zero discrimination.)
• | Good: 'Same crew that ran Fort Stewart custodial (W912HN-22-C-0014) — 96.3% CPARS rating across 18 months, zero customer complaints, completed first-day phase-in with full crew.' (Specific contract, specific number, specific outcome.)
• | Better: same line plus a proof point in column E: 'CPARS letter on file dated Apr 14, 2026; available to evaluator on request.' Now an evaluator can verify it without asking.
What 'Reviewed' really means
• | Not: the writer thinks they are done.
• | Not: the proposal manager skimmed it.
• | Is: a color team reviewer (Pink, Red, or Gold) read it, scored it, wrote comments, and the writer incorporated those comments and confirmed the changes back to the reviewer.
• | If that loop hasn't closed, status is 'Complete' — not 'Reviewed'. The difference matters at Gold Team.
Common compliance gaps to look for
• | Forgotten sub-clauses: L.4.1 lists three sub-requirements (a)(b)(c) and your matrix only has one row for L.4.1. Add (a), (b), (c) as separate rows.
• | Page-limit miscounts: cover page, TOC, dividers, and required forms are usually excluded — check Section L. If you assume they count and the RFP says they don't, you wrote ten extra pages for nothing.
• | Missing certifications: FAR 52.204-8 (Reps and Certs) and SF-33 signatures get forgotten because they live in Section J, not L. Put a row for each in your matrix anyway.
• | Time-zone errors: federal deadlines are almost always Eastern Time. Saw a Pacific-coast offeror miss a 17:00 ET deadline by three hours because they thought it was 17:00 PT. The portal closed. They lost.
When to start this matrix
• | On RFP release day. Not 'after the kickoff meeting'. Not 'when the writers are assigned'. On release day.
• | If you started after release day on a 30-day proposal, you're already two days behind. Backfill the matrix tonight and run a quick gap scan tomorrow morning.
• | On a 60-day proposal: matrix done by day 3, Pink Team scored by day 30, Red Team by day 45, Gold Team by day 55.
Operator note (Sergio): in Afghan infantry we ran a checklist before every patrol — boots, comms, ammo count, medkit, route brief. Same item every time. Same person checking. We didn't skip any of it because the day we skipped one was the day it mattered. Same logic for the Submission Checklist tab. Don't skip lines because 'we always get that one right'.